## Sheet1
Agile Product Backlog(Traffic Safety App)
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Route Optimization and Real Time Traffic Updates | Yes | Yes | High | In Progress | 16.5 | Yes
Building GUI | No | Yes | High | Complete | 5 | No
Loading the map | No | Yes | High | Complete | 2 | No
Showing route on map | No | Yes | Medium | Complete | 5 | No
adding direction steps | No | No | High | In Progress | 1 | Yes
Displaying traffic data on the route | No | No | High | In Progress | 0.5 | Yes
Live navigation | No | No | High | In Progress | 3 | No
Driver Awareness | Yes | No | High | In Progress | 23 | Yes
Tracking GPS location of driver | No | No | Medium | Complete | 5 | Yes
Provide auditory alerts at intersections, sharp curves, pedestrian crossings, or other potential hazards | No | Yes | High | Complete | 10 | No
Speed Limit notification | No | Yes | Medium | Complete | 3 | No
Analyze driver behaviour and provide feedback | No | No | Medium | In Progress | 5 | Yes
Emergency Assistance | Yes | No | Medium | Complete | 20 | No
Building Authentication | No | No | Low | Complete | 2 | No
Collecting contacts | No | Yes | Medium | Complete | 2 | No
sending SMS and call to 112 | No | No | Medium | Complete | 16 | No
Report | Yes | Yes | Medium | In Progress | 3 | Yes
Intializing Firebase | No | Yes | Medium | Complete | 1 | No
Sending user Fcm token to db | No | Yes | Low | Complete | 1 | No
Send notification to all users | No | Yes | High | Complete | 1 | No
Education and Training | No | No | Medium | Not Started | 9 | No
Collect data from feedback table | No | No | Medium | Not Started | 2 | No
fetch relavent resources based on feedback | No | No | High | Not Started | 5 | No
Display to user | No | No | High | Not Started | 2 | No
Create a Product Backlog in Smartsheet

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started